## Sheet1
Sprint Backlog
Wed 17th Sept 2014 - Wed 24th Sept 2014 | [11 empty] | To Do
In Progress
1) Searchable glossary of potato disease symptoms and futher information page linking to these symptoms | Duration time in hours | Who | Status | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Done
In app database set up | 4 | Mark | Done | 0
Custom list view adapter for glossary | 6 | Robert | Done | 3
Futher information page layout | 1 | Liu | Done | 0
Image scrollable slideshow with image enlarged when clicked for futher information page | 4 | Kari | Done | 0
Merge image scrollable slideshow and format info page layout | 2 | Kari | In Progress | 2
Organising/enter data for database and images into res folder for the glossary. | 6 |  | To Do | 6
Connecting database data to custom list view adapter | 6 |  | To Do | 6
Connecting database data to futher information page | 4 |  | To Do | 4
UI changes - Including tabs | 7 |  | To Do | 7
Search in the glossary | 2 |  | To Do | 2
Order glossary by catergory | 3 |  | To Do | 3
Category screen
| Duration time in hours | Who | Status | Mon | Tue | Wed | Thurs | Friday | Sat | Sun | Mon
2) An expert system to diagnose potato disease symptoms | 8 | Ewan | In Progress | 1
Mock expert system | 4 |  | To Do | 4
Organising/enter data into database for expert system once available | 5 |  | To Do | 5
Changing mock expert system to real expert system when data is available and in database | 2 |  | To Do | 2
Linking expert system's final suggestion to futher information page | 4 |  | To Do | 4
UI changes | 4 |  | To Do | 4
| Duration time in hours | Who | Status | Mon | Tue | Wed | Thurs | Friday | Sat | Sun | Mon
Additional Tasks Over Project | Ongoing | Kari - Writes Up | In Progress | N/A
SCRUM Videos or minutes to document daily meetings. | Not for this sprint - listed as reminder | N/A | To Do | N/A
Research competitor apps and use for evaluation againist ours | Ongoing | All | In Progress | N/A
Github Updates | 2 | All | To Do | 2
Sprint Review Prep | 1 | All | To Do | 1
Sprint Retrospective | 6 |  | To Do | 6
Unit tests and proof of them passing | Not for this sprint - listed as reminder | N/A | To Do | N/A
Proof of Agile Approach | Not for this sprint - listed as reminder | N/A | To Do | N/A
Presentation writing | Not for this sprint - listed as reminder | N/A | To Do | N/A
Burndown chart | 2 |  | To Do | 2
Refactioring | 6 |  | To Do | 6
Testing On Phone | Ongoing | All | In Progress | N/A
Ethics Form | 5 | Kari | In Progress | 1
Risk Management/Assessment Spreadsheet For Team | 2 | Kari | In Progress | 1
Final Team Report demonstrating software engineering - Appendix containing user guide + relevant source code | Ongoing | Kari | To Do | N/A
Proof of application and software engineering design | Not for this sprint - listed as reminder | N/A | To Do | N/A
Usability evaluation | Not for this sprint - listed as reminder | N/A | To Do | N/A
Video demo/user guide | Ongoing | All | To Do | N/A
Weekly Individual Reflection Diary
Total Hours Remaining | 96
*** Calculation based on initial tasks without additional added