## Sheet1
Risk | Likelihood | Loss | Severity | Priority | Prevention 1 | Prevention 2
Team members continually not attending meetings | 8 | 9 | 72 | 1 | Have a minutes document to track each meeting and if a pattern emerges then contact the team member about the situation | If prevention 1 doesn't work, then speak to a lecturer immediately and draw their attention to this or get team leader to discuss at managerial meetings
Being unable to contact team members | 7 | 9 | 63 | 2 | Try to reach the team member through mobile, facebook and email. If pattern emerges, raise your concerns with this member | If prevention 1 doesn't work, then speak to a lecturer immediately and draw their attention to this or get team leader to discuss at managerial meetings
Areas of the project taking longer that expected | 7 | 8 | 56 | 3 | Try to over estimate time to spend on tasks, so this situation does not happen | If prevention 1 doesn't work, then set more team members on the task, to try minimise the time
Team members unable to attend meetings | 8 | 7 | 56 | 3 | Have team members make sure to contact before meetings letting members know ahead of time so they can prepare for this scenario | If prevention 1 doesn’t work, then contact the team member with details of what they missed and the tasks they have been set
Lack of continual software testing | 7 | 8 | 56 | 3 | Have one team member overview testing and make sure things are constantly being tested by members in the team | If prevention 1 doesn't work, then allocate a day or team for the team to do through testing on whats been done so far to catch up
Lack of clarification on team members tasks/responsibilities | 6 | 9 | 54 | 4 | Make clear the task allocation at every meeting and on the minutes document so everyone knows where they stand. | If prevention 1 doesn't work, then said team member should contact other team members to ask them about the allocation from last meeting
Unable to meet client frequently | 7 | 7 | 49 | 5 | Try to set up cover this by frequent meetings via email, skype or longer meetings when possible. | If issues are still occuring after preventation 1 then make clear to lecturer that frequent meetings mean you aren't getting frequent feedback hence you may have an inaccurate representation of what client wants
Client changing specifications | 6 | 8 | 48 | 6 | Constantly speak to the client so you are constantly aware of what they want from the specifications throughout project | If prevention 1 doesn't work, then make sure there is allocated time at the end of project (like a week - 2 weeks) to make any last min additions
Team members falling ill | 6 | 8 | 48 | 6 | Do not allocate large amounts of work to anyone person and make sure there is always updated verisions of everyones files on dropbox | If prevention 1 has not happened, then have all members contact details, so you will be able to contact them to get files or info on what stage they are at
Miscommunication of ideas and general direction of project | 5 | 8 | 40 | 7 | Have lots of meetings, communication and documentation, so team members are constantly aware of what is going on. Ideally check work the morning of each day | If prevention 1 doesn't work, speak to lecturer about the miscommunication and how to handle it or get team leader to discuss at managerial meetings
Requirements/user stories are misunderstood | 4 | 9 | 36 | 8 | All group members shall agree and have input in requirements/user stories then evaluate at them at almost every meeting
Holidays affecting project work | 4 | 9 | 36 | 8 | Over estimate how long tasks will take, so there is some room to give or take in terms of holidays | If prevention 1 doesn't work, then have team members agree to meetings on holidays as well
Unable to access critical files | 4 | 8 | 32 | 9 | Use dropbox to store files so they are accessible off campus and make sure at least one member has all files on a USB/Hard drive | If prevention 1 doesn't work, then make sure you have everyones contact details so you can get the files from this person
Plans and estimates based on unreliable information | 4 | 8 | 32 | 10 | Have many team meetings and discussions with client frequently so everyone is clear on the information
Loss of data | 3 | 9 | 27 | 11 | Make sure all updated files are on dropbox and backed up on usb or hard drive as well
Quality control is not present by all team members | 3 | 8 | 24 | 12 | Each team member should overview all aspects of the project before anything is considered done. | If prevention 1 doesn't work, then have all group members checking over each members new piece of work as soon as it's submitted to dropbox
Weather causing issues travelling | 3 | 6 | 18 | 13 | Team members should try and contact in advance they won't make it to meetings and post all critical files on dropbox or github | If prevention 1 doesn't work, make sure you have contact details and so you can try get the files or what they are working on in another form
Completion date is changed | 2 | 9 | 18 | 13 | Start work early so we will be ahead of the project deadline
Industry standards change | 3 | 4 | 12 | 14 | Double check information on standards before starting the project | If prevention 1 doesn't work, have team members looking out for changes in standards as project goes along