## Sheet1
Sprint Backlog
Thurs 25th Sept 2014 - Thurs 2nd Oct 2014
To Do
1) Sprint 1 Feedback Changes | Duration time in hours | Who | Status | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs | In Progress
Change images and text on glossary page to just images (possibly change to grid view ) | 4 | Kari | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Done
Remove descriptions under video or make shorter | 1 | Kari | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Build mock website* | 6 | Mark | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Search by - Name | 1 | Robert | Done | 1 | 1 | 1 | 1 | 4 | 0 | 0 | 0
Email Prof Torrance | 1 | Kari | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2) An expert system to diagnose potato disease symptoms | Duration time in hours | Who | Status | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs
Organising/enter data into database for expert system once available | 4 | Ewan | Done | 4 | 4 | 4 | 4 | 2 | 2 | 0 | 0
Changing mock expert system to real expert system when data is available and in database | 5 | Ewan | Done | 5 | 5 | 5 | 5 | 5 | 5 | 0 | 0
Linking expert system's final suggestion to futher information page | 2 | Ewan | Done | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0
UI changes | 4 | Ewan | Done | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
3) The ability to update the app | Duration time in hours | Who | Status | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs
Build mock website* | 6 | Mark | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Connect mock website to database | 8 | Kari | Done | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Connect websites server to app to enable update | 12 | Mark/Kari | Done | 12 | 12 | 12 | 12 | 10 | 6 | 0 | 0
UI changes | 8 | All | Done | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0
Blob changes in the application | 6 | Mark | Done | ~ | 6 | 6 | 0 | 0 | 0 | 0 | 0
Additional Tasks | Duration time in hours | Who | Status | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | Thurs
Report | 12 | Kari | In Progress | 12 | 12 | 12 | 6 | 6 | 6 | 4 | 2
User manual or video | 4 | Kari, Robert,Mark | Done | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0
Minutes | Ongoing | Kari | Done | N/a | N/a | N/a | N/a | N/a | N/a | N/a | N/a
Usability evaluation | 3 | All | Done | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0
User testing | 3 | All | Done | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 0
Testing on phone | Ongoing | All | Done | N/a | N/a | N/a | N/a | N/a | N/a | N/a | N/a
Presentation writing | 4 | Kari, Robert,Mark | Done | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 0
Presentation prep | 3 | All | To Do | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
Sprint retrospective | 1 | All | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
Burndown chart | 2 | N/a | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Unit testing | 6 | N/a | To Do | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Refactoring / Commenting / Liscensing | 5 | Robert | Done | 5 | 5 | 5 | 5 | 5 | 5 | 2 | 0
Build log book | 4 | Kari | In Progress | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 1
Binding report | 2 | All | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Appendix disks - Move git etc onto disks | 4 | Kari | In Progress | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 1
Total Time | 121 |  |  | 101 | 97 | 95 | 79 | 78 | 66 | 37 | 17