## Sheet1
Sprint Backlog
Wed 17th Sept 2014 - Wed 24th Sept 2014
To Do
1) Searchable glossary of potato disease symptoms and futher information page linking to these symptoms | Duration time in hours | Who | Status | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed | In Progress
In app database set up | 4 | Mark | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Done
Custom list view adapter for glossary | 6 | Robert | Done | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Further information page layout | 1 | Liu | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Image scrollable slideshow with image enlarged when clicked for futher information page | 4 | Kari | Done | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Merge image scrollable slideshow and format info page layout | 2 | Kari | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Organising/enter data for database and images into res folder for the glossary. | 6 | Mark,Kari | In Progress | 6 | 6 | 6 | 6 | 6 | 2 | 1
Connecting database data to custom list view adapter | 6 | Mark,Kari | Done | 6 | 6 | 6 | 6 | 6 | 6 | 0 | 0
Connecting database data to futher information page | 4 | Mark,Kari | Done | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
UI changes - Including tabs | 7 | Mark,Kari | In Progress | 7 | 7 | 3 | 3 | 3 | 3 | 1
Search in the glossary | 2 | Robert | In Progress | 2 | 2 | 2 | 2 | 2 | 1 | 1
Pinch zoom images | 2 | Kari | In Progress | 2 | 1 | 1 | 1 | 1 | 1 | 1
Circle icons images | 2 | Kari | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Category screen | 1 | Robert | Done | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
2) Video Tutorials of the fields tests | Duration time in hours | Who | Status | Wed | Thurs | Fri | Sat | Sun | Mon | Tue | Wed
Basic video example in android | 3 | Liu | Done | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Merge video example into app | 4 | Kari | Done | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Place Lesleys videos in the app this includes compression | 3 | Kari | Done | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
UI style | 2 | Kari | In Progress | 2 | 2 | 2 | 2 | 2 | 2 | 1
2) An expert system to diagnose potato disease symptoms | Duration time in hours | Who | Status | Wed | Thurs | Friday | Sat | Sun | Mon | Tue | Wed
Mock expert system | 8 | Ewan | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Organising/enter data into database for expert system once available | 4 | Ewan,Mark | In Progress | 4 | 4 | 4 | 4 | 4 | 4 | 4
Changing mock expert system to real expert system when data is available and in database | 5 |  | To Do | 5 | 5 | 5 | 5 | 5 | 5 | 5
Linking expert system's final suggestion to futher information page | 2 |  | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2
UI changes | 4 |  | To Do | 4 | 4 | 4 | 4 | 4 | 4 | 4
Mock expert system in android | 4 |  | To Do | 4 | 4 | 4 | 4 | 4 | 4 | 4
| 6 | Ewan | Done | 6 | 6 | 5 | 5 | 5 | 3 | 0 | 0
Additional Tasks Over Project | Duration time in hours | Who | Status | Wed | Thurs | Friday | Sat | Sun | Mon | Tue | Wed
SCRUM Videos or minutes to document daily meetings. | Ongoing | Kari - Writes Up | In Progress | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Research competitor apps and use for evaluation againist ours | Not for this sprint - listed as reminder | N/A | To Do | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Github Updates | Ongoing | All | In Progress | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Sprint Review Prep | 2 | All | To Do | 2 | 2 | 2 | 2 | 2 | 2 | 2
Sprint Retrospective | 1 | All | To Do | 1 | 1 | 1 | 1 | 1 | 1 | 1
Unit tests and proof of them passing | 6 |  | To Do | 6 | 6 | 6 | 6 | 6 | 6
Proof of Agile Approach | Not for this sprint - listed as reminder | N/A | To Do | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Presentation writing | Not for this sprint - listed as reminder | N/A | To Do | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Burndown chart | 2 | 2 | To Do | 2 | 2 | 2 | 2 | 2 | 2
Refactioring | 6 | 6 | To Do | 6 | 6 | 6 | 6 | 6 | 6
Testing On Phone | Ongoing | All | To Do | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Ethics Form | 5 | Kari | Done | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
Risk Management/Assessment Spreadsheet For Team | 2 | Kari | Done | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Final Team Report demonstrating software engineering - Appendix containing user guide + relevant source code | Ongoing | Kari | To Do | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Proof of application and software engineering design | Ongoing | Kari | To Do | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Usability evaluation | Not for this sprint - listed as reminder | N/A | To Do | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Video demo/user guide | Not for this sprint - listed as reminder | N/A | To Do | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Weekly Individual Reflection Diary | Ongoing | All | To Do | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Total Hours Remaining | 110
*** Calculation based on initial tasks without additional added